## HSE-Activities-Main
Activity ID | Activity Type | Title/Description | Category | Location | Department | Responsible Person | Scheduled Date | Actual Date | Start Time | End Time | Status | Key Observations | Action Items | Action Owner | Deadline for Actions | Completion Status | Compliance Standard | Risk Level | Incidents Reported? | Incident Description | Lessons Learned | Supporting Documents | Reported By | Approval Status
ACT001 | BOG Visit | Executive Safety Walkthrough | Leadership | Main Office | HSE | John Smith | 2023-03-15 | 2023-03-15 | 9:00 | 11:30 | Completed | PPE compliance 92% | Improve signage in Zone 4 | Sarah Lee | 2023-03-30 | Completed | OSHA Standards | Medium | No | - | Leadership visibility improves compliance | BOG_Report_001.pdf | Alex Wong | Approved
ACT002 | Drills (Emergency) | Fire Evacuation Drill - Admin Building | Safety | Admin Building | Facilities | Mike Chen | 2023-04-05 | 2023-04-05 | 10:00 | 10:45 | Completed | 5 mins over target time | Retrain evacuation routes | James Brown | 2023-04-20 | In Progress | NFPA 70E | High | No | - | Need clearer assembly point signs | Drill_Log_002.pdf | Lisa Wang | Approved | Count Participants for Each Activity | 2
ACT003 | L3 Audit | Annual Process Safety Audit | Compliance | Plant Area A | Operations | Audit Team | 2023-05-10 | 2023-05-12 | 8:00 | 16:00 | Completed | 3 major findings | Update lockout-tagout procedures | David Wilson | 2023-06-30 | Pending | Not in the list | High | No | - | Need more frequent LOTO training | Audit_Report_003.pdf | Emma Garcia | Pending | Count Present Participants | 2
ACT004 | Weekly HSE Meeting | Contractor Safety Performance Review | Operational | Conference Rm | HSE | Sarah Lee | Every Monday | 2023-04-17 | 14:00 | 15:30 | Ongoing | 2 contractors below KPIs | Issue warning letters | John Smith | 2023-04-24 | In Progress | Not in the list | Low | No | - | Weekly reviews reduce incidents | Meeting_Min_004.docx | Mike Chen | Approved | Average Engagement Score | 4.5
ACT005 | Site Live Coaching | Scaffolding Safety Demonstration | Training | Construction | HSE | James Brown | 2023-04-22 | 2023-04-22 | 7:30 | 9:00 | Completed | 100% participation | - | - | - | - | OSHA Standards | Medium | No | - | Hands-on training most effective | Coaching_005.mp4 | Lisa Wang | Approved
ACT006 | PTW Panel Assessment | High-Risk Work Permit Review | Compliance | Control Room | Operations | David Wilson | 2023-04-28 | 2023-04-28 | 8:30 | 10:00 | Completed | 2 permits missing JSA | Implement digital checklist | Emma Garcia | 2023-05-15 | Completed | Not in the list | High | Yes | Near-miss during welding | Need better hazard identification | PTW_Log_006.xlsx | John Smith | Approved
ACT007 | Morning Site Engagement | Daily Toolbox Talk - Electrical Safety | Safety | Site East | Electrical | Alex Wong | Daily | 2023-05-03 | 6:30 | 6:45 | Completed | Good crew participation | - | - | - | - | OSHA Standards | Low | No | - | Short daily talks improve awareness | TBT_007.pdf | Mike Chen | Approved
ACT008 | Incident Investigation | Fall Protection Near-Miss Follow-up | Risk Assessment | Platform B | HSE | Sarah Lee | 2023-05-05 | 2023-05-08 | 9:00 | 11:00 | Completed | Harness inspection overdue | Replace 5 damaged harnesses | James Brown | 2023-05-20 | Completed | OSHA Standards | High | Yes | Worker slipped but harness saved | Equipment checks critical | Inv_Report_008.pdf | Lisa Wang | Approved
ACT009 | Drivers' Forum | "Darb Salama" Monthly Safety Briefing | Safety | Parking Lot | Logistics | Mike Chen | 2023-05-15 | 2023-05-15 | 7:00 | 8:00 | Completed | 3 drivers with speeding violations | Schedule refresher training | David Wilson | 2023-05-30 | In Progress | ISO 45001 | Medium | No | - | Gamification improves engagement | Forum_Notes_009.docx | Emma Garcia | Approved
ACT010 | HSE Recognition | Q2 Safety Star Awards | Recognition | Main Hall | HR | John Smith | 2023-05-20 | 2023-05-20 | 16:00 | 17:30 | Completed | Record 12 nominations | Expand recognition program | Sarah Lee | 2023-06-30 | Pending | Not in the list | Low | No | - | Public recognition motivates teams | Awards_List_010.pdf | Alex Wong | Approved
ACT011 | Stand-Down | Safety Stand-Down After Incident | Safety | Site Wide | HSE | James Brown | 2023-05-25 | 2023-05-25 | 7:00 | 8:30 | Completed | Full site participation | Review working at height procedures | David Wilson | 2023-06-10 | Completed | OSHA Standards | High | Yes | Fall incident (no injury) | Reinforce safety culture after incidents | StandDown_011.pdf | Sarah Lee | Approved
ACT012 | FLS Session | Frontline Supervisor Coaching | Training | Workshop | Operations | Emma Garcia | 2023-06-01 | 2023-06-01 | 10:00 | 12:00 | Completed | Identified 3 communication gaps | Develop FLS handbook | Alex Wong | 2023-06-30 | In Progress | Not in the list | Medium | No | - | Standardized tools improve FLS effectiveness | FLS_Report_012.pdf | Mike Chen | Approved
ACT013 | Mustead Workshop | Hazard Identification Training | Training | Training Room | HSE | John Smith | 2023-06-08 | 2023-06-08 | 9:00 | 15:00 | Completed | 87% competency improvement | Roll out to all contractors | Sarah Lee | 2023-07-30 | Pending | OSHA Standards | Medium | No | - | Interactive training boosts retention | Workshop_013.pptx | James Brown | Approved
ACT014 | Contractor HSE Review | Monthly Contractor Performance Review | Contractor | Conference Rm | HSE | Lisa Wang | 2023-06-15 | 2023-06-15 | 14:00 | 16:00 | Completed | 2 contractors on watchlist | Implement improvement plans | Mike Chen | 2023-06-30 | In Progress | Not in the list | High | No | - | Monthly reviews prevent complacency | Contractor_014.xlsx | David Wilson | Approved
ACT015 | Risk Assessment Workshop | JSA Development for New Equipment | Risk Assessment | Engineering | Operations | Alex Wong | 2023-06-20 | 2023-06-20 | 8:30 | 12:30 | Completed | Identified 12 new hazards | Update equipment manuals | Emma Garcia | 2023-07-15 | Pending | ANSI/ASSE Z10 | High | No | - | Multidisciplinary teams yield best results | RA_Report_015.pdf | John Smith | Approved
ACT016 | Meeting | Worker Accommodation Inspection | Health | Camp Site | HR | Sarah Lee | 2023-06-22 | 2023-06-22 | 15:00 | 16:30 | Completed | AC units need servicing | Schedule maintenance | James Brown | 2023-06-30 | Completed | Not in the list | Low | No | - | Regular welfare checks improve morale | Welfare_016.pdf | Lisa Wang | Approved
ACT017 | Inspections (Including CMT) | Critical Maintenance Task Verification | Compliance | Plant Area B | Maintenance | David Wilson | 2023-06-25 | 2023-06-25 | 7:00 | 10:00 | Completed | 3 tasks overdue | Implement tracking system | Mike Chen | 2023-07-15 | In Progress | ANSI/ASSE Z10 | High | No | - | Digital tracking prevents misses | CMT_Report_017.pdf | Emma Garcia | Approved
ACT018 | Ad-hoc Visit | CEO Impromptu Site Visit | Leadership | Construction | HSE | John Smith | 2023-06-28 | 2023-06-28 | 11:00 | 12:30 | Completed | Positive feedback on housekeeping | Recognize Zone 3 team | Sarah Lee | 2023-07-05 | Completed | Not in the list | Low | No | - | Leadership engagement boosts morale | Visit_Notes_018.docx | James Brown | Approved
ACT019 | Monthly Safety Meeting | July Safety Performance Review | Operational | Main Hall | HSE | Lisa Wang | 2023-07-01 | 2023-07-01 | 9:00 | 11:00 | Completed | TRIR improved by 15% | Focus on near-miss reporting | David Wilson | 2023-07-31 | In Progress | OSHA Standards | Medium | No | - | Data-driven discussions most effective | Meeting_Min_019.pdf | Mike Chen | Approved
ACT020 | Competency Assessment | Crane Operator Certification | Training | Workshop | Operations | Emma Garcia | 2023-07-05 | 2023-07-05 | 8:00 | 17:00 | Completed | 4 operators need retraining | Schedule refresher courses | Alex Wong | 2023-07-30 | Pending | Not in the list | High | No | - | Annual assessments maintain standards | Assessment_020.pdf | John Smith | Approved

## Participants
Activity ID | Participant Name | Role | Department | Contact Number | Email | Attendance Status | Check- In time | Check-Out Time | Engagement Score | Feedback | Notes
ACT001 | Robert Johnson | Site Manager | Operations | +968 9123 4567 | r.johnson@company.com | Present | 8:55 | 11:35 | 5 | "Executive engagement sets strong safety tone" | Took detailed notes
ACT001 | Sarah Al-Maskari | HSE Officer | HSE | +968 9876 5432 | s.almaskari@company.com | Present | 8:50 | 11:40 | 4 | "Suggest more frequent leadership walks" | Documented observations
ACT002 | Ali Hassan | Fire Warden | Facilities | +968 9234 5678 | a.hassan@company.com | Present | 9:55 | 10:50 | 3 | "Need clearer evacuation route markers" | Assisted with drill
ACT002 | Fatima Al-Balushi | Admin Staff | HR | +968 9456 7890 | f.balushi@company.com | Late | 10:15 | 10:40 | 2 | "Didn't hear initial alarm" | Needs retraining
ACT003 | David Wilson | Lead Auditor | Quality | +968 9112 2334 | d.wilson@company.com | Present | 7:55 | 16:05 | 5 | "Process safety culture needs improvement" | Main audit lead
ACT003 | Khalid Al-Harthy | Process Engineer | Engineering | +968 9334 4556 | k.alharthy@company.com | Present | 8:10 | 15:50 | 4 | "Will implement LOTO improvements" | Technical specialist
ACT004 | James Brown | Contractor Supervisor | Construction | +968 9777 8888 | j.brown@contractor.com | Present | 13:55 | 15:25 | 3 | "Our safety stats improved this month" | Brought performance data
ACT005 | Mohammed Ali | Scaffold Crew | Construction | +968 9666 7777 | m.ali@contractor.com | Present | 7:25 | 9:05 | 5 | "Best hands-on training I've had" | Volunteer demonstrator
ACT006 | Emma Garcia | Permit Coordinator | Operations | +968 9555 6666 | e.garcia@company.com | Present | 8:25 | 9:55 | 4 | "Digital checklist will prevent errors" | Suggested template
ACT007 | Raj Patel | Electrician | Electrical | +968 9444 5555 | r.patel@contractor.com | Present | 6:25 | 6:50 | 4 | "Daily reminders help" | Asked good questions
ACT008 | Lisa Wang | Incident Investigator | HSE | +968 9333 4444 | l.wang@company.com | Present | 8:55 | 11:05 | 5 | "Root cause: inadequate equipment inspection system" | Lead investigator
ACT009 | Ahmed Al-Rashidi | Truck Driver | Logistics | +968 9222 3333 | a.rashidi@company.com | Present | 6:55 | 8:05 | 3 | "Understood speeding consequences" | Previous violator
ACT010 | Susan Taylor | HR Director | HR | +968 9888 9999 | s.taylor@company.com | Present | 15:55 | 17:35 | 5 | "Recognition program boosts morale" | Presented awards
ACT011 | Carlos Mendez | Crane Operator | Construction | +968 9111 2222 | c.mendez@contractor.com | Present | 6:55 | 8:35 | 4 | "Will reinforce harness checks" | Near-miss involved
ACT012 | Youssef Al-Kindi | Shift Supervisor | Operations | +968 9776 6555 | y.alkindi@company.com | Present | 9:55 | 11:55 | 5 | "FLS handbook will standardize our approach" | Contributed examples
ACT013 | Priya Sharma | HSE Trainer | HSE | +968 9332 2111 | p.sharma@company.com | Present | 8:55 | 14:55 | 5 | "Participants engaged well with VR hazards" | Delivered workshop
ACT014 | Omar Al-Farsi | Contractor HSE Manager | Construction | +968 9443 3222 | o.alfarsi@contractor.com | Present | 13:55 | 15:55 | 3 | "Working on corrective actions" | Provided improvement plan
ACT015 | Thomas Muller | Risk Engineer | Engineering | +968 9554 4333 | t.muller@company.com | Present | 8:25 | 12:35 | 4 | "New equipment requires updated risk matrix" | Technical lead
ACT016 | Aisha Al-Jabri | Camp Administrator | HR | +968 9665 5444 | a.aljabri@company.com | Present | 14:55 | 16:25 | 3 | "Will schedule AC maintenance this week" | Responsible for facility
ACT017 | Peter Kowalski | Maintenance Lead | Maintenance | +968 9775 5666 | p.kowalski@company.com | Present | 6:55 | 9:55 | 4 | "Digital tracking will prevent overdue CMTs" | System superuser

## Activity type
Activity
Meeting
Coaching
Training
Inspection
Audit
BOG Visit
L3 Audits
L2 Audits
Inspections (Including CMT)
Campaigns
Drills (Emergency)
Events
Stand-Downs
Monthly Meetings
Weekly HSE Integration Meetings
Weekly Progress Meetings
Total South HSE Meeting
Drivers' Forum - "Darb Salama"
Welfare Meetings
HSE Recognition (Awards & Rewards)
PTW Panel Assessments
FLS (Front Line Supervision)
Mustead Workshop
Site Effectiveness
One-to-One Sessions
Contractor HSE Monitoring Plan Review
Incident Investigation - Follow-up & Close-out
Site Live Coaching
Ad-hoc Visits
Morning Site Engagement
Facilitating Leadership Visits
Interfacing with MCPH
Risk Assessment Workshops
Competency Assessments
PIM Management

## Status
Planned
Ongoing
Completed
Postponed
Cancelled

## Completion Status
Pending
In Progress
Completed

## Risk Level
Low
Medium
High

## Approval Status
Approved
Pending
Rejected

## Category
Safety
Environment
Compliance
Health
Risk Assessment
Leadership
Contractor
Recognition
Operational
Competency
Training